## Summary
Reports
Sl. No. | Activity
|  |  | Selection: | Project Name
A | No. of PR planned for release V/s Actual Release
| (For BU user, design user, design approver, Procurement user, buyer user, commercial approver user) | SL. No. | Job Code | Job Description | No. of PRs Planned | No. of PRs Released | No. of planned Orders | NO of Actual order settlement
|  | 1 | ACDFGC | XXCHYD | 23 | 9 | 14 | 5
B | List of PRs which are delayed beyond schedule/ List of PR to be released for given month | Selection: Project name & month
| (For BU user, design user, design approver, Procurement user, buyer user, commercial approver user) | SL. No. | Job Code | PR Details | Scheduled date | Delay (in days) | Remarks
|  | 1 | ACDFGC
|  | 2 | ACDFGC
|  | 3 | ACDFGC
C | List of POs which are delayed beyond schedule/List of PO to be released for given month | Selection: Project name & month
| (For BU user, design user, design approver, Procurement user, buyer user, commercial approver user) | SL. No. | Job Code | Item Description Details | Qty. | Scheduled date | Delay (in days) | Remarks
|  | 1 | ACDFGC
|  | 2 | ACDFGC
|  | 3 | ACDFGC
D | List of PRs/Items which are Technically Cleared but Ordering is pending | Selection: | Project Name
| ( BU user, Procurement user, buyer user, commercial approver user) | SL. No. | Job Code | Item Description Details | Qty. | Technical Clearance date | Target Ordering date | Remarks
|  | 1 | ACDFGC
|  | 2 | ACDFGC
|  | 3 | ACDFGC
E | Report to Extract data of desired columns of Sheet " Procurement & Projects"
( BU user, Procurement user, buyer user, commercial approver user)
F | Provision of Downloading data of each Templates in Excel file
|  | Selection: | Project Name, buyer Name, month selection
G | Status of PRs - Buyer wise (If a buyer name is selected then for a given project or for all project pending PO should appear there} Buyer Productivity Analysis (BPA) | SL. No. | Job Code | Buyer Name | Item Description Details | Qty. | PR Actual received date (from procurement user) | Enquiry floating date | No. of Offers received | Actual Technical Clearance date | L2 Schedule Ordering date | Actual Ordering date | Delay in days | Supplier Name | Basic Order Value | Ace | Saving
|  | 1 | ACDFGC | TTT | [6 empty] | 2019-03-30 | 2019-05-14 | 45
| ( Procurement user, buyer user, commercial approver user) | 2 | ACDFGC | TTT
|  | 3 | ACDFGC | TTT
I | New order book | (BU user, Procurement User, Buyer user, Commercial comitee members)
M | Procurement & projects | (BU user, Procurement User, Buyer user, Commercial comitee members)
N | Supplier Performance Report (SPR) | (BU user, Procurement User, Buyer user, Commercial comitee members)
O | year-wise material Price trend (MPT) | (BU user, Procurement User, Buyer user, Commercial comitee members)
P | Supplier Specific spend (SSS) | (BU user, Procurement User, Buyer user, Commercial comitee members)
Q | Design Dept. Productivity (DDP) | (BU user, design user, design approver user, Procurement User, Buyer user, Commercial comitee members)
L | Project Financials | (BU user, Procurement User, Buyer user, Commercial comitee members)
Note on F8: Clicking this those PRs which were supposed to release will come
Note on G8: Clicking this PRs which are already released will come.
Note on H8: Clicking this would provide list of Pos planned
Note on I8: Clicking this should give details of POs

## New Order Book
All ongoing Project details
Currency: | INR
Sl. No. | Job Code | Job Desciption | LOI date | Contract Signing date | Contract value | Supply Order Value | Contract Start Date | Contractual Completion date | Contract Duration | Remarks | Target date of Completion | Actual Completion date

## Procurement & Projects
Sl. No. | Section Details Area | BU Person Coordinator | Item/Activity Description | PR No. | Released by (design User) | Approved by | PR L2 Schedule Release date | Actual Receipt date PR release Date | PR Received date in Purchase (by procurement User) | Assigned Buyer Name | Enquiry floating date | Bidder 1 Name / date of Offer receipt | Bidder 1 L&T Comments date Vendor Reply Tech. Clearance | Bidder 2 Name / date of Offer receipt | Bidder 2 L&T Comments date Vendor Reply Tech. Clearance | Bidder 3 Name / date of Offer receipt | Bidder 3 L&T Comments date Vendor Reply Tech. Clearance | Bidder 4 Name / date of Offer receipt | Bidder 4 L&T Comments date Vendor Reply Tech. Clearance | Bidder 5 Name / date of Offer receipt | Bidder 5 L&T Comments date Vendor Reply Tech. Clearance | No. of Offers recd. | Planned Technical Clearance date (No input is given in the platform) | Actual Technical Clearance date (Is it vendor specific?) | Commercial Closure date (No input is given in the platform) | L2 Schedule Ordering date (No input is given in the platform) | Target date of Ordering (No input is given in the platform) | LOI | LOI Date | LOI Basic Value | Supplier Name/Address and Contact details | PO No. | PO Date | PO Type Domestic or Import | Delivery Date as per PO | Remarks - Purchase (Items left out for Ordering ..etc) | BG Submission | Advance payment date | Drg. Submission date | Drg approval date | Mfg Clearance | Inspection Call date | Inspection Call Remarks | Inspection clearance date | Inspection Clearance Remarks | Despatch Clearance | Despatch Clearance Remarks | Qty Receipt at site | Qty Pending | Supply Completion Yes/No | Remarks - Projects | ACE (Basic Value) in Rs. L | Invoice value Gross in Rs. L | Ordered Value Basic Value in Rs. L | Cost Saving
[52 empty] | 120 |  | 100 | 20
To be captured from design data
Data to be entered by Procurement dept
Project Team

## SPR
Supplier Performance Report (SPR)
Selection section: |  |  | Search Section:
Start date: |  |  | Supplier Name:
End date
Supplier Name | Project Name | PO No | PO Date | Order Basic Value | Delay in BG submission (in Days) | Delay in drawing submission (in days) | Delay in Delivery (In days)
STX | P1 | 123 | 2017-04-25 | 23000 | 10 | 3 | 26
| P2 | 234 | 2018-03-02 | 24000 | 12 | 4 | 30
| P1 | 235 | 2018-10-14 | 24500 | 13 | 10 | 32
| P3 | 345 | 2019-02-01 | 19000 | 2 | 20 | 18
| P4 | 236 | 2019-03-13 | 32876 | 0 | 21 | 39
Average Delay in BG submission (in Days) |  |  | 7.4
Average Delay in drawing submission (in days) |  |  | 11.6
Average Delay in Delivery (In days) |  |  | 29

## MPT
Material Price trend (MPT)
Selection section: |  |  |  |  | Search Section:
Start date: |  |  |  |  | Material Name Or Material Code:
End date
[5 empty] | No. of order: | 5 | Average Value: | 21318
Material Code | Material Name | PO No | UOM | Qty. | PO date | Order Basic Value of the item | Project Name | Supplier Name | total PO basic Value
ABC | Telephone | x1 | No. | 1000 | 2012-04-25 | 20034 | SAIL | S12 | 20034000
|  | x2 | No. | 2700 | 2013-04-25 | 21000 | GAIL | S32 | 56700000
|  | s1 | No. | 2400 | 2014-04-25 | 20056 | BSP | S12 | 48134400
|  | s2 | No. | 1290 | 2015-04-25 | 22000 | SAIL | S12 | 28380000
|  | f1 | No. | 1865 | 2017-04-25 | 23500 | BSP | S12 | 43827500

## SSS
Supplier Specific spend (SSS)
Selection section:
Start date:
End date
Supplier Name: | [6 empty] | Total No. of PO: | 5 |  | Total Ordered value: | 123376
Supplier Name | Project Name | Item Name | PO No | PO date | Year | PO basic Value | Saving Against ACE | Competitor-1 Price (basic) | Competitor-2 Price (basic) | Competitor-3 Price (basic) | Competitor-4 Price (basic)
ABC | P1a | Cable-LT | P1 | 2017-04-25 | 2017 | 23000 | 100
| P1b | Cable-HT | P2 | 2018-03-02 | 2018 | 24000 | 102
| P1a | Cable-LT | P3 | 2018-10-14 | 2018 | 24500 | 10
| P1b | Cable-Wire | P4 | 2019-02-01 | 2019 | 19000 | -1
| P1b | Overhead Wie | P5 | 2019-03-13 | 2019 | 32876 | 45

## DDP
Design Dept. Productivity (DDP)
Selection section:
Project Name:
Design User name:
Start date
End date
Case-1
If only "Project Name" gets selected
Project Name | Design User Name | Approved By: (design approver's Name) | Item Name | Scheduled PR date | Actual PR released date | Delay in PR release (in days) | Scheduled Technical clearance (TC) date | Actual Technical clearance (TC) date | Delay in technical clearance (in days) | Post order Actual drawing/datasheet submission date | Final Drg. No. | Scheduled manufacturing date | Actual Manufacturing clearance date. | Delay in giving manufacturing clearance. | Remarks (issue faced)
PRS | Rakesh |  | Chair | 2017-03-20 | 2017-04-25 | 36 | 2017-03-20 | 2017-04-25 | 36 | 2017-03-20 |  | 2017-03-20 | 2017-04-25 | 36
| Mohan |  | Table | 2018-01-10 | 2018-03-02 | 51 | 2018-01-10 | 2018-03-02 | 51 | 2018-01-10 |  | 2018-01-10 | 2018-03-02 | 51
| Raj |  | door | 2018-04-02 | 2018-04-03 | 1 | 2018-04-02 | 2018-04-03 | 1 | 2018-04-02 |  | 2018-04-02 | 2018-04-03 | 1
| Dinesh |  | Window | 2018-11-22 | 2018-12-01 | 9 | 2018-11-22 | 2018-12-01 | 9 | 2018-11-22 |  | 2018-11-22 | 2018-12-01 | 9
| Ganesh |  | Cement | 2018-12-15 |  | Delayed | 2018-12-15 |  | Delayed | 2018-12-15 |  | 2018-12-15 |  | Delayed
| Mohan |  | Sand | 2019-01-10 |  | Delayed | 2019-01-10 |  | Delayed | 2019-01-10 |  | 2019-01-10 |  | Delayed
| Dinesh |  | telephone | 2019-01-19 |  | Delayed | 2019-01-19 |  | Delayed | 2019-01-19 |  | 2019-01-19 |  | Delayed
| Ganesh |  | sensor | 2019-02-16 |  | Delayed | 2019-02-16 |  | Delayed | 2019-02-16 |  | 2019-02-16 |  | Delayed
| Raj |  | cable | 2019-03-18 |  | Delayed | 2019-03-18 |  | Delayed | 2019-03-18 |  | 2019-03-18 |  | Delayed
1-a: PR status Report
Total no of Items: | 9
PR released: | 4
PR not released: | 5
Technical cleared Items | 4
Pending technical clearance | 5
No of Items which got Manufacturing clearance | 4
No of Items waiting for Manufacturing clearance | 5
1. B: Design User wise PR allocation:
Rakesh: | 1
Mohan | 2
Raj | 2
Dinesh | 2
Ganesh | 2
Total: | 9
Case-2
If only "Design user Name" gets selected
Design User Name | Project Name | Approved By: (design approver's Name) | Item Name | Scheduled PR date | Actual PR released date | Delay in PR release (in days) | Scheduled Technical clearance (TC) date | Actual Technical clearance (TC) date | Delay in technical clearance (in days) | Post order Actual drawing/datasheet submission date | Final Drg. No. | Scheduled manufacturing date | Actual Manufacturing clearance date. | Delay in giving manufacturing clearance. | Remarks (issue faced)
Rakesh | SAIL |  | Chair | 2017-03-20 | 2017-04-25 | 36 | 2017-03-20 | 2017-04-25 | 36 | 2017-03-20 |  | 2017-03-20 | 2017-04-25 | 36
| SAIL |  | Table | 2018-01-10 | 2018-03-02 | 51 | 2018-01-10 | 2018-03-02 | 51 | 2018-01-10 |  | 2018-01-10 | 2018-03-02 | 51
| SAIL |  | door | 2018-04-02 |  | Delayed | 2018-04-02 |  | Delayed | 2018-04-02 |  | 2018-04-02 |  | Delayed
| Vedanta |  | Window | 2018-11-22 | 2018-12-01 | 9 | 2018-11-22 | 2018-12-01 | 9 | 2018-11-22 |  | 2018-11-22 | 2018-12-01 | 9
| Vedanta |  | Cement | 2018-12-15 |  | Delayed | 2018-12-15 |  | Delayed | 2018-12-15 |  | 2018-12-15 |  | Delayed
| Vedanta |  | Sand | 2019-01-10 |  | Delayed | 2019-01-10 |  | Delayed | 2019-01-10 |  | 2019-01-10 |  | Delayed
| Vedanta |  | telephone | 2019-01-19 |  | Delayed | 2019-01-19 |  | Delayed | 2019-01-19 |  | 2019-01-19 |  | Delayed
| Vedanta |  | sensor | 2019-02-16 | 2019-02-15 | -1 | 2019-02-16 | 2019-02-15 | -1 | 2019-02-16 |  | 2019-02-16 | 2019-02-18 | 2
| Vedanta |  | cable | 2019-03-18 | 2019-03-15 | -3 | 2019-03-18 | 2019-04-17 | 30 | 2019-03-18 |  | 2019-03-18 |  | Delayed
Items handled in each projects
SAIL | [6 empty] | Vedanta
Total PR handled | 3 | [5 empty] | Total PR handled | 6
PR already released | 2 | [5 empty] | PR already released | 3
Pending PRs to be released | 1 | [5 empty] | Pending PRs to be released | 3
Items pending for technical clearance: | 1 | [5 empty] | Items pending for technical clearance: | 3
Items pending for manufacturing clearance: | 1 | [5 empty] | Items pending for manufacturing clearance: | 4
Case-3:
If both "Project name" & "Design user Name" gets selected
Design User Name | Project Name | Approved By: (design approver's Name) | Item Name | Scheduled PR date | Actual PR released date | Delay in PR release (in days) | Scheduled Technical clearance (TC) date | Actual Technical clearance (TC) date | Delay in technical clearance (in days) | Post order Actual drawing/datasheet submission date | Final Drg. No. | Scheduled manufacturing date | Actual Manufacturing clearance date. | Delay in giving manufacturing clearance. | Remarks (issue faced)
Rakesh | Vedanta |  | Window | 2018-11-22 | 2018-12-01 | 9 | 2018-11-22 | 2018-12-01 | 9 | 2018-11-22 |  | 2018-11-22 | 2018-12-01 | 9
|  |  | Cement | 2018-12-15 |  | Delayed | 2018-12-15 |  | Delayed | 2018-12-15 |  | 2018-12-15 |  | Delayed
|  |  | Sand | 2019-01-10 |  | Delayed | 2019-01-10 |  | Delayed | 2019-01-10 |  | 2019-01-10 |  | Delayed
|  |  | telephone | 2019-01-19 | 2019-02-19 | 31 | 2019-01-19 |  | Delayed | 2019-01-19 |  | 2019-01-19 |  | Delayed
|  |  | sensor | 2019-02-16 | 2019-02-15 | -1 | 2019-02-16 | 2019-02-15 | -1 | 2019-02-16 |  | 2019-02-16 | 2019-02-18 | 2
|  |  | cable | 2019-03-18 | 2019-03-15 | -3 | 2019-03-18 | 2019-04-17 | 30 | 2019-03-18 |  | 2019-03-18 |  | Delayed
Vedanta
Total PR handled | 6
PR already released | 4
Pending PRs to be released | 2
Items pending for technical clearance: | 3
Items pending for manufacturing clearance: | 4

## Project Financial Milestone
Below Entry would be Job Code wise
Sl. No. | Activity | Planned Contractual date | Target date of Completion | Actual Completion date